## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As an analyst, I want chat transcripts to be ingested automatically so that support conversations are available for audit review. | Must | Customer chat export access | Vaidehi | Done
Sprint 1 | Sprint 1 | US-02 | As a reviewer, I want audio calls transcribed with speaker labels so that call quality can be evaluated consistently. | Must | Whisper / STT integration | Siri | Done
Sprint 1 | Sprint 1 | US-03 | As a team lead, I want transcript cleanup and normalization so that LLM prompts receive clean structured input. | Must | Transcript schema finalization | Gayathri | Done
Sprint 2 | Sprint 2 | US-04 | As a supervisor, I want empathy, compliance, and resolution scoring so that each interaction gets a quality score. | Must | Prompt template approval | Siri | Done
Sprint 2 | Sprint 2 | US-05 | As an auditor, I want issue categories to be extracted from conversations so that repeated customer pain points can be tracked. | Should | Scoring engine baseline | Vaidehi | Done
Sprint 2 | Sprint 2 | US-06 | As a manager, I want escalations and non-compliance phrases flagged so that risky conversations are reviewed quickly. | Must | LLM issue classification | Gayathri | In Progress
Sprint 3 | Sprint 3 | US-07 | As an auditor, I want policy documents indexed in a vector store so that conversation checks can use contextual retrieval. | Must | Policy documents collection | Vaidehi | In Progress
Sprint 3 | Sprint 3 | US-08 | As a supervisor, I want a dashboard showing agent-wise quality trends so that low-performing cases are visible in one place. | Must | Scoring outputs available | Gayathri | In Progress
Sprint 3 | Sprint 3 | US-09 | As an operations lead, I want filtering by agent, date, and issue type so that dashboard analysis is faster. | Should | Dashboard base UI | Siri | To Do
Sprint 4 | Sprint 4 | US-10 | As a supervisor, I want instant alerts for severe compliance issues so that action can be taken without delay. | Must | Issue severity rules | Siri | To Do
Sprint 4 | Sprint 4 | US-11 | As a manager, I want PDF and Excel report exports so that weekly review summaries can be shared with leadership. | Should | Dashboard metrics finalized | Gayathri | To Do
Sprint 4 | Sprint 4 | US-12 | As a product owner, I want the platform deployed with logging and monitoring so that the solution is ready for demo and evaluation. | Must | Deployment environment setup | Vaidehi | To Do
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 137 | 32 | 30 | 30 | 22 | 5 | 2 | 2 | 1 | 2 | 1 | 3 | 2 | 3 | 2
SPRINT 1 BACKLOG
US-01 | T-101 | Set up project repo, folders, and sample chat dataset | 2026-02-04 | 2026-02-06 | Vaidehi | Setup | Completed | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0
US-02 | T-102 | Integrate Whisper/OpenAI STT for audio transcription pipeline | 2026-02-10 | 2026-02-15 | Siri | Development | Completed | 8 | 1 | 1 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1
US-03 | T-103 | Create transcript cleaning script and standardized JSON schema | 2026-02-18 | 2026-02-23 | Gayathri | Development | Completed | 5 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1
US-01 | T-104 | Validate sample outputs with 10 chat and 5 call transcripts | 2026-02-24 | 2026-02-25 | Vaidehi | Testing | Completed | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
US-03 | T-105 | Document ingestion flow and milestone 1 demo notes | 2026-02-25 | 2026-02-28 | Gayathri | Documentation | Completed | 4 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-04 | T-201 | Design scoring rubric for empathy, compliance, and resolution | 2026-03-01 | 2026-03-04 | Siri | Design | Completed | 7 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
US-04 | T-202 | Build prompt templates and scoring function for transcript review | 2026-03-05 | 2026-03-08 | Siri | Development | Completed | 5 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
US-05 | T-203 | Add issue extraction labels for refund, escalation, and delay cases | 2026-03-09 | 2026-03-11 | Vaidehi | Development | Completed | 7 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
US-06 | T-204 | Implement non-compliance keyword and severity tagging logic | 2026-03-12 | 2026-03-14 | Gayathri | Development | In Progress | 9 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-205 | Run scoring validation on pilot transcripts and tune prompt wording | 2026-03-15 | 2026-03-17 | Vaidehi | Testing | Completed | 6 | 2 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-07 | T-301 | Prepare policy documents and FAQ content for vector indexing | 2026-03-17 | 2026-03-17 | Vaidehi | Preparation | Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-302 | Integrate LangChain with Pinecone for contextual retrieval | 2026-03-17 | 2026-03-17 | Vaidehi | Development | In Progress | 12 | 3 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-303 | Build dashboard layout with score cards and trend widgets | 2026-03-17 | 2026-03-17 | Gayathri | Development | In Progress | 10 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-304 | Add filters for agent, issue type, and audit date range | 2026-03-17 | 2026-03-17 | Gayathri | Development | To Do | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-305 | Connect dashboard charts to scored interaction dataset | 2026-03-17 | 2026-03-17 | Siri | Integration | To Do | 7 | 2 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US-10 | T-401 | Configure alert rules for severe compliance and escalation issues | 2026-03-18 | 2026-04-18 | Siri | Configuration | To Do | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-402 | Generate weekly PDF and Excel export templates for supervisors | 2026-03-19 | 2026-03-19 | Gayathri | Development | To Do | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T-403 | Prepare deployment environment and environment variables | 2026-03-19 | 2026-03-19 | Vaidehi | Deployment | To Do | 7 | 2 | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T-404 | Add logging, exception handling, and monitoring checkpoints | 2026-03-19 | 2026-03-19 | Vaidehi | Development | To Do | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-405 | Complete end-to-end demo walkthrough and release checklist | 2026-03-19 | 2026-03-19 | Gayathri | Testing | To Do | 5 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Audio samples had inconsistent volume levels | Normalized sample set and updated preprocessing script
Sprint 1 | Day 5 | Transcript schema fields were missing agent metadata | Added agent_id and call_channel fields to schema
Sprint 2 | Day 3 | Scoring prompt was overrating neutral conversations | Reworked examples and added stricter rubric wording
Sprint 2 | Day 7 | Issue tags overlapped for escalation and compliance | Created separate severity mapping for each label
Sprint 3 | Day 2 | Policy PDF text extraction produced noisy chunks | Switched to cleaned text extraction before embedding
Sprint 3 | Day 6 | Dashboard API response was slow for trend charts | Added caching for aggregated score metrics
Sprint 4 | Day 4 | Export template columns were misaligned in Excel report | Updated report formatter and retested with sample data
Sprint 4 | Day 8 | Alert rule triggered duplicate notifications | Introduced cooldown logic for repeated high-risk cases

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-04 | 2026-03-04 | Siri | Break transcription work into smaller validation tasks | Starting integration before sample cleanup is complete | Pair review for core pipeline changes | Used checkpoint demos after transcription module completion
2 | Sprint 1 | 2026-02-05 | 2026-02-05 | Vaidehi | Track sample data assumptions in one place | Manual file renaming during ingestion testing | Quick standup updates on blockers | Created a common sample-data folder for the team
3 | Sprint 1 | 2026-02-09 | 2026-02-12 | Gayathri | Add schema review before coding downstream logic | Changing transcript fields without notifying others | Writing short implementation notes | Shared final schema sheet with all team members
4 | Sprint 2 | 2026-02-16 | 2026-02-18 | Siri | Test prompt quality with edge-case transcripts earlier | Using a single prompt for all issue types | Baseline metric comparison after every prompt change | Created separate prompt variants for scoring and issue extraction
5 | Sprint 2 | 2026-02-23 | 2026-02-25 | Vaidehi | Collect more failure examples from validation set | Waiting until sprint end to review false positives | Frequent peer testing on scored outputs | Prepared a mini error log for calibration
6 | Sprint 2 | 2026-02-28 | 2026-03-03 | Gayathri | Document label definitions before implementation | Mixing severity rules with business issue tags | Structured weekly demos | Updated scoring glossary used by the whole team
7 | Sprint 3 | 2026-03-04 | 2026-03-06 | Siri | Add retrieval relevance checks in every build | Embedding documents without chunk-level review | Daily sync on integration progress | Added retrieval sanity tests for policy queries
8 | Sprint 3 | 2026-03-08 | 2026-03-11 | Vaidehi | Prepare dashboard sample data before UI review | Late sharing of chart-ready aggregated data | Reusable metric definitions | Published dashboard-ready CSV snapshots for faster UI work
9 | Sprint 3 | 2026-03-15 | 2026-03-17 | Gayathri | Review dashboard usability with filters earlier | Crowding too many KPIs into one page | Keeping feedback from mentor discussions | Simplified dashboard into summary and detail sections
10 | Sprint 4 | 2026-03-18 | 2026-03-20 | Siri | Finalize alert thresholds with sample scenarios | Leaving deployment checks to the last day | Maintaining a release checklist | Added alert test matrix before final integration
11 | Sprint 4 | 2026-03-22 | 2026-03-23 | Vaidehi | Log deployment issues immediately during setup | Manual environment changes without notes | Cross-checking endpoints before demos | Prepared deployment notes and rollback points
12 | Sprint 4 | 2026-03-23 | 2026-03-23 | Gayathri | Review report export format with supervisor expectations | Hardcoding labels in export sheet | Writing concise demo summaries | Aligned report columns with dashboard metrics