## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Setup project environment and integrate Whisper/OpenAI STT for chat & call transcription | MUST HAVE | OpenAI API key, Whisper library setup | Akshayaa Maharshi | Completed
S1 | S1 | US-002 | Clean and normalize transcripts into structured schema | MUST HAVE | Transcript output from STT module | Akshayaa Maharshi | Completed
S2 | S2 | US-003 | Build LLM-based quality scoring engine (empathy, compliance, resolution) | MUST HAVE | Structured transcript data | Akshayaa Maharshi | Completed
S2 | S2 | US-004 | Implement compliance violation detection and improvement suggestions | MUST HAVE | LLM scoring logic and policy rules | Prajakta Sawant | Completed
S3 | S3 | US-005 | Integrate RAG pipeline using LangChain and FAISS/Pinecone | SHOULD HAVE | Clean transcripts and policy documents | Akshayaa Maharshi | Completed
S3 | S3 | US-006 | Connect policy documents for context-aware auditing | MUST HAVE | RAG pipeline setup and document embeddings | Prajakta Sawant | Completed
S4 | S4 | US-007 | Build dashboard for supervisors (agent-wise performance analytics) | SHOULD HAVE | Quality scoring output data | Akshayaa Maharshi Prajakta Sawant | Completed
S4 | S4 | US-008 | Visualize compliance trends and quality scores | SHOULD HAVE | Dashboard backend data integration | Akshayaa Maharshi | Completed
S5 | S5 | US-009 | Implement real-time compliance alerts | MUST HAVE | Compliance detection engine | Akshayaa Maharshi Prajakta Sawant | Completed
S5 | S5 | US-010 | Generate downloadable PDF and Excel reports | SHOULD HAVE | Scoring results and dashboard data | Prajakta Sawant | Completed
S6 | S6 | US-011 | Deploy system on cloud (Streamlit/Render/AWS) | MUST HAVE | Fully integrated system and environment configuration | Akshayaa Maharshi | Completed
S6 | S6 | US-012 | Perform final testing and optimization | MUST HAVE | Deployed application build | Prajakta Sawant, Akshayaa Maharshi | Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 58 | 14.5 | 12 | 16.5 | 8.5 | 3.5 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Setup project environment and dependency configuration | 2025-12-29 | 2025-12-30 | Akshayaa Maharshi | Coding / Research | Completed | 3 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Integrate Whisper/OpenAI STT for audio transcription | 2025-12-31 | 2026-01-02 | Prajakta Sawant | Speech-to-text API integration and dependency configuration | Completed | 4.5 | 2 | 1 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 3 | Clean and normalize transcripts into structured schema | 2026-01-03 | 2026-01-05 | Prajakta Sawant Akshayaa Maharshi | Coding | Completed | 3.5 | 2 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 4 | Build LLM-based quality scoring engine (empathy, compliance, resolution) | 2026-01-06 | 2026-01-08 | Akshayaa Maharshi | Coding | Completed | 5 | 2 | 0.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 5 | Implement compliance violation detection and improvement | 2026-01-09 | 2026-01-12 | Prajakta Sawant | Coding / Research | Completed | 4.5 | 1 | 2 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | 6 | Integrate RAG pipeline using LangChain and FAISS/Pinecone | 2026-01-12 | 2026-01-16 | Akshayaa Maharshi Prajakta Sawant | Coding / Research | Completed | 7 | 1 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | 7 | Connect policy documents for context-aware auditing | 2026-01-17 | 2026-01-20 | Prajakta Sawant | Coding / Research | Completed | 6 | 1 | 2 | 0.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | 8 | Build Streamlit dashboard for supervisors | 2026-01-21 | 2026-01-25 | Akshayaa Maharshi | Coding | Completed | 4 | 0.5 | 0 | 1 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | 9 | Visualize compliance trends and agent-wise performance metrics | 2026-01-27 | 2026-01-31 | Prajakta Sawant Akshayaa Maharshi | Coding / Research | Completed | 2 | 0 | 0 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | 10 | Implement real-time compliance alerts for policy violations | 2026-02-01 | 2026-02-08 | Akshayaa Maharshi | Coding / Research | Completed | 8 | 1 | 0.5 | 2 | 0 | 1.5 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | 11 | Enable PDF and Excel report generation for audit outputs | 2026-02-09 | 2026-02-12 | Prajakta Sawant | Coding | Completed | 2 | 1 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | 12 | Deploy the AI Quality Auditor platform on Streamlit Cloud | 2026-02-16 | 2026-02-19 | Akshayaa Maharshi Prajakta Sawant | Deployment / Integration | Completed | 3.5 | 1 | 1 | 0.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | 13 | Perform final testing, bug fixes, and performance optimization | 2026-02-20 | 2026-02-22 | Prajakta Sawant Akshayaa Maharshi | Testing / Optimization | Completed | 5 | 0.5 | 2.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Uncertainty in selecting an appropriate modular project structure for scalable AI integration. | Discussed architectural options with team and finalized a layered structure separating ingestion, AI engine, and UI components.
Sprint 1 | Day 4 | Initial issues while configuring dependencies for OpenAI and Whisper integration. | Resolved version conflicts and verified installation through sample API calls.
Sprint 2 | Day 7 | Whisper transcription accuracy varied for noisy audio samples. | Tested multiple preprocessing techniques and validated results with different sample inputs.
Sprint 2 | Day 9 | Delay in handling larger audio files during testing. | Limited audio length for initial testing and optimized workflow for batch processing.
Sprint 3 | Day 12 | Raw transcripts had inconsistent speaker tagging and timestamps. | Developed normalization logic to standardize speaker labels and conversation flow.
Sprint 3 | Day 14 | Difficulty defining metadata structure for downstream LLM processing. | Finalized structured JSON schema after reviewing use cases for scoring and compliance analysis.
Sprint 4 | Day 18 | Unclear measurable definition of empathy and resolution quality | Researched QA evaluation metrics and created scoring rubric aligned with support standards.
Sprint 4 | Day 20 | LLM responses were inconsistent in output format. | Improved prompt engineering by enforcing structured response format.
Sprint 5 | Day 24 | Compliance violations were not consistently detected. | Added explicit rule-based constraints within prompt and tested with sample policy violations.
Sprint 5 | Day 27 | Difficulty balancing strict compliance scoring with contextual flexibility. | Fine-tuned prompts with example-based guidance to improve contextual understanding.
Sprint 6 | Day 30 | Low relevance in retrieved policy documents. | Adjusted document chunking size and embedding configuration to improve retrieval accuracy.
Sprint 6 | Day 33 | Integration complexity between retrieval pipeline and scoring engine. | Refactored pipeline flow to ensure retrieved context is injected properly into LLM prompts.
Sprint 7 | Day 38 | Difficulty representing multiple agent metrics in a simple dashboard view. | Redesigned dashboard layout to prioritize key KPIs and improve visualization clarity.
Sprint 7 | Day 41 | Real-time update delay in visual components. | Optimized backend response flow and reduced unnecessary data refresh cycles.
Sprint 8 | Day 45 | Configuration conflicts during deployment. | Standardized environment configuration and validated deployment on staging before final release.
Sprint 8 | Day 48 | Issues generating downloadable PDF/Excel reports. | Debugged report formatting logic and ensured proper export functionality.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-12-29 | 2026-01-04 | Prajakta Sawant, Akshayaa Maharshi | Documenting setup steps clearly from beginning. | Assuming API configurations will work without testing. | Discussing technical doubts openly within team. | Resolved version conflicts and verified setup with sample API calls.
2 | Sprint 2 | 2026-01-05 | 2026-01-12 | Akshayaa Maharshi | Validating transcription output with multiple test cases. | Relying on single audio sample for testing. | Improving coordination during integration tasks. | Optimized file handling and limited initial test size for validation.
3 | Sprint 3 | 2026-01-13 | 2026-01-20 | Prajakta Sawant | Structuring data properly before LLM integration. | Handling raw transcripts without preprocessing. | Reviewing schema decisions before finalizing. | Standardized speaker labels and cleaned transcript structure.
4 | Sprint 4 | 2026-01-21 | 2026-01-31 | Akshayaa Maharshi Prajakta Sawant | Refining prompts to get consistent scoring output. | Keeping prompts too generic. | Testing LLM responses with different scenarios. | Refined prompt structure to enforce formatted responses.
5 | Sprint 5 | 2026-02-01 | 2026-02-08 | Prajakta Sawant | Cross-checking compliance logic with policy rules. | Overlooking minor policy violations in testing. | Improving prompt clarity for better accuracy. | Added clearer policy rules within prompt logic.
6 | Sprint 6 | 2026-02-09 | 2026-02-15 | Akshayaa Maharshi Prajakta Sawant | Fine-tuning document chunking for better retrieval. | Using large document chunks without validation. | Collaborating during integration debugging. | Adjusted document chunk size and re-tested embeddings.
7 | Sprint 7 | 2026-02-16 | 2026-02-19 | Akshayaa Maharshi | Simplifying dashboard metrics for clarity. | Overloading UI with unnecessary graphs. | Focusing on usability and readability. | Simplified KPIs and reorganized visual components.
8 | Sprint 8 | 2026-02-20 | 2026-02-22 | Prajakta Sawant, Akshayaa Maharshi | Testing deployment in staging before final release. | Direct deployment without environment verification. | Final validation and performance optimization. | Aligned package versions and redeployed after testing.